| SECTION OVERVIEW |  | #### SECTION IS RESPONSIBLE FOR COLLECTING, ASSEMBLING, AND REPORTING ALL INCIDENT STATUS INFORMATION AND FORECASTING RESPONSE NEEDS #### ELEMENTS INCLUDE: #### Prepares and distributes the Incident Action Plan and facilitates the Tactics and Planning meetings. #### Collect, evaluate, analyze, display, and disseminate incident information and status of all assigned and available resources #### Functions as the primary support for decision-making to the overall emergency organization #### Provides anticipatory appraisals and develops plans necessary to cope with changing events |  |
| --- | --- | --- | --- |
| POSITION OVERVIEW |  | #### Manages the collection, documentation, evaluation, forecasting, dissemination and use of information about the development of the incident and status of resources |  |
| REPORT | TO | #### MANAGEMENT ¦ EOC DIRECTOR |  |
| REPORT | TO ME | STAFF - Resource Unit Leader - Situation Unit Leader - Documentation Unit Leader - Demobilization Unit Leader |  |
| PLANS & REPORTS |  | - EOC ACTION PLAN ¦ OVERSEES DEVELOPMENT - ADVANCE PLANS ¦ OVERSEES DEVELOPMENT - SITUATIONAL REPORTS ¦ OVERSEES DEVELOPMENT - SITUATIONAL STATUS DISPLAY ¦ OVERSEES DEVELOPMENT - ESSENTIAL ELEMENTS OF INFORMATION ¦ OVERSEES DEVELOPMENT - DATA AND INFORMATION COLLECTION PLAN ¦ OVERSEES DEVELOPMENT - OPERATION SECTION REPORTS ¦ OVERSEES COMPILATION & DISTRIBUTION - LOCAL GOVERNMENT AFTER ACTION REPORT ¦ SUPPORTS DEVELOPMENT - AGENCY ADMINISTRATOR REPORT ¦ OVERSEES DEVELOPMENT |  |
| FORMS |  | - POSITION JOB AID FOLDER - ICS-201 INCIDENT BRIEFING - ICS-202 INCIDENT OBJECTIVES - ICS-203- ORGANIZATIONAL LIST - ICS-205A COMMUNICATION LIST - ICS-207 ORGANIZATION CHART - ICS-209 INCIDENT STATUS SUMMARY - ICS-211 CHECK-IN LIST | - ICS-214 ACTIVITY LOG - ICS-215 OPERATIONAL PLANNING WORKSHEET - ICS-215A SAFETY ANALYSIS - ICS-226 FOR PD CREDENTIALING - ICS-230 DAILY MEETING SCHEDULE |
| WORKSTATION |  | EOC PLANNING SECTION |  |

Additional Duties:

- Provide leadership and direction to assigned staff

- Manage all assigned personnel

- Ensure section is able to meet deadlines

- Facilitate all meetings and briefings

- Ensure open communication with between Sections and Command Staff

- Ensure all work products are completed

Meetings:

| TIME |  |
| --- | --- |
|  | Command and General Staff Meeting |
|  | Tactics Meeting |
|  | Planning Meeting |
|  | Operational Period Briefing |
|  | Transfer of Command Briefing |
|  | Additional meetings/briefings by invite |

| TIME |  |  |  | #### STATUS |
| --- | --- | --- | --- | --- |
| DUTIES |  |  |  |  |
|  |  |  | Establish the appropriate level of staffing and organization for the Section. |  |
|  |  |  | Exercise overall responsibility for the coordination of unit activities within the section. |  |
|  |  |  | Supervise the Planning Section. |  |
|  |  |  | Ensure that the following responsibilities of the Section are addressed as required: - Collect, analyze, and display situation information - Prepare periodic Situation Report - Preparing and distributing the EOC Action Plan and facilitating the Action Planning meeting - Conducting Advance Planning activities and report - Providing technical support services to the various EOC sections and branches, and documenting and maintaining files on all EOC activities |  |
|  |  |  | In coordination with the other Section Coordinators, ensure that Status Reports are completed and utilized as a basis for Situation Analysis Reports, and the EOC Action Plan. |  |
|  |  |  | Keep the EOC Director informed of significant issues affecting the P&I Section |  |
| ACTIVATION |  |  |  |  |
|  |  |  | Check in at the EOC - (FORM ¦ ICS-211, FORM ¦ ICS-205A) |  |
|  |  |  | Assist with EOC Set-up (If not already fully set-up) |  |
|  |  |  | Receive situation, section and position briefing, initial EOC Director objectives, and next meeting/briefing schedule from available and appropriate personnel. |  |
|  |  |  | Meet Planning staff, when assigned, ensure they receive initial brief, establish work assignments for initial operating period. |  |
|  |  |  | Ensure readiness to maintain concise records of position activities - (FORM ¦ ICS-214) |  |
|  |  |  | Within 90 minutes, ensure sufficient staff is available for a 24-hour schedule, or as required |  |
|  |  |  | Ensure that the Planning Section is set up properly and that appropriate personnel, equipment, and supplies are in place, including maps and status boards |  |
|  |  |  | Based on the situation, activate positions/unit within the section as needed: - Resource Unit Leader - Situation Unit Leader - Documentation Unit Leader - Demobilization Unit Leader |  |
|  |  |  | Participate in Command and General Staff meeting, Tactics meeting, Planning meeting, Incident Action Plan approval process, and Operational briefing. |  |
|  |  |  | Meet with all Section Chiefs and ensure responsibilities are clearly understood. |  |
|  |  |  | - Develop specific tactics and strategies to meet larger Unified Command Objectives |  |
|  |  |  | Meet with all Unit Leaders and ensure responsibilities are clearly understood |  |
|  |  |  | - Establish contact with the Operational Area EOC when activated. - Coordinate Situation Analysis Reports with their Planning Section. - (FORM ¦ ICS-209 OR REPORT ¦ SITUATION STATUS) |  |
|  |  |  | Meet with Operations Section Chief; obtain and review any major incident reports. - (REPORT ¦OPS ________ STATUS REPORT) |  |
|  |  |  | - Make a list of key issues to be addressed by Planning; in consultation with section staff. - Identify objectives to be accomplished during the initial Operational Period. - (FORM ¦ ICS-202) |  |
| RESPONSE |  |  |  |  |
|  |  |  | Identify key issues currently affecting the Planning Section; meet with section personnel and determine appropriate section objectives for the first operational period. |  |
|  |  |  | Ensure all assigned personnel establish and maintain individual position logs and other necessary files (assign a scribe as necessary). - (FORM ¦ ICS 214) |  |
|  |  |  | Ensure that The Situation Unit is maintaining current information for the situation analysis report. |  |
|  |  |  | Ensure that major incidents reports and status reports are completed by the Operations Section and are accessible by the Planning Section |  |
|  |  |  | Ensure that a situation analysis report is produced and distributed to EOC Sections and the Operational Area EOC at least once, prior to the end of the operational period. - (FORM ¦ ICS-209 or REPORT ¦ SITUATION STATUS) |  |
|  |  |  | Ensure that all status boards and other displays are kept current and that posted information is neat and legible. |  |
|  |  |  | Ensure that the Public Information Officer has immediate and unlimited access to all status reports and displays. |  |
|  |  |  | Conduct periodic briefings with section staff and work to reach consensus among staff on section objectives for forthcoming operational periods. - (FORM ¦ ICS-201) |  |
|  |  |  | Facilitate the EOC Director's Action Planning meetings approximately two hours before the end of each operational period. - (FORM ¦ ICS-230) |  |
|  |  |  | Ensure that objectives for each section are completed, collected and posted in preparation for the next Action Planning meeting. |  |
|  |  |  | Ensure that the EOC Action Plan is completed and distributed prior to the start of the next operational period. - (FORMS ¦ ICS-201, ICS-202, ICS-205A, ICS-207, ICS-208, ICS-211, ICS-213. ICS-215, ICS-215A, ICS-230 or PLAN ¦ EOC ACTION PLAN) |  |
|  |  |  | Work closely with each unit within the Planning Section to ensure the section objectives, as defined in the current EOC Action Plan, are being addressed. |  |
|  |  |  | Ensure that the Documentation Unit maintains files on all EOC activities and provides reproduction and archiving services for the EOC, as required. |  |
|  |  |  | Ensure that all media contacts are referred to the Public Information Officer. |  |
|  |  |  | Ensure that fiscal and administrative requirements are coordinated through the Finance/ Administration Section (notification of emergency expenditures and daily time sheets). |  |
|  |  |  | Brief the EOC Director on all major incidents. |  |
|  |  |  | Brief Unit Leaders periodically on any updated information you may have received. |  |
|  |  |  | Share status information with other sections as appropriate. |  |
| SHIFT CHANGE/TRANSFER OF DUTIES |  |  |  |  |
|  |  |  | Provide turnover briefing to position replacement. |  |
|  |  |  | Provide details regarding ongoing activities and planned activities to be accomplished during the upcoming operational period. - (FORM ¦ USE CURRENT POSITION JOBAID) - (FORM ¦ USE CURRENT ICS-214) |  |
|  |  |  | Provide all completed documentation to the Documentation Unit |  |
|  |  |  | Follow EOC check out procedures, including signing out, workstation clean-up and forwarding phone number where you can be reached. - (FORM ¦ ICS-211, FORM ¦ ICS-205A) |  |
| DEMOBILIZATION |  |  |  |  |
|  |  |  | Ensure adequate staffing patterns prior to demobilization. |  |
|  |  |  | Deactivate position when authorized by EOC Director and follow Demobilization Unit Leader directions/plan. |  |
|  |  |  | - Complete all required forms, reports, and other documentation. - Provide all completed documentation to the Documentation Unit, prior to your departure. - Turn over financial information to Finance/Administration Section Chief. |  |
|  |  |  | Develop Demobilization plan with Planning and Operations Section. |  |
|  |  |  | Ensure all personnel being released are completing appropriate paperwork. - (FORM ¦ ICS 214) |  |
|  |  |  | If Mutual Aid resources were used, release personnel and equipment as appropriate. |  |
|  |  |  | Provide a forwarding phone number where you can be reached. |  |
|  |  |  | Be prepared to provide input to the after-action report. |  |

Additional Duties:

- Provide leadership and direction to assigned staff

- Manage all assigned personnel

- Ensure section is able to meet deadlines

- Facilitate all meetings and briefings

- Ensure open communication with between Sections and Command Staff

- Ensure all work products are completed

| TASKS (PENDING) |  |  |  |
| --- | --- | --- | --- |
| NOTES |  |  |  |
| Name: |  | Forwarding Phone #: | _______________________ |
| Date: |  | Time: | ________________am / pm |